## TASK
task_code | status_code | wbs_id | task_name | base_drtn_hr_cnt | succ_list | pred_list | base_start_date | base_end_date | act_start_date | act_end_date | resource_list | projwbs__status_code | complete_pct | base_cost | act_cost | total_float_hr_cnt | sv | cv | etc | critical_flag | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | (*)BL Project Duration(h) | (*)Successors | (*)Predecessors | (*)BL Project Start | (*)BL Project Finish | Actual Start | Actual Finish | (*)Resources | (*)Project Status | Activity % Complete(%) | (*)BL Project Total Cost($) | (*)Actual Total Cost($) | (*)Total Float(h) | (*)Schedule Variance($) | (*)Cost Variance($) | (*)Estimate To Complete($) | (*)Critical | Delete This Row
EC1000 | Completed | EC00515.D&E | Design Building Addition | 55 | EC1030 | EC1010 | 2010-11-01 08:00 | 2011-01-17 09:36 | 2010-11-01 08:00 | 2011-01-19 09:36 | Paul Kim, Paul Kim | Active | 100 | 26496 | 89100 |  | 0 | -62604 | 0 | N
EC1170 | In Progress | EC00515.Int-Finish.Coverings | Prepare and Solicit Bids for Flooring | 24 | EC1250 | EC1080 | 2011-03-21 15:24 | 2011-04-22 15:24 | 2011-04-04 15:38 |  | Project Controls, Project Controls | Active | 95 | 5280 | 12375 | 218 | -264 | -7359 | 651.32 | N
EC1250 | Not Started | EC00515.Int-Finish.Coverings | Review Bids for Flooring | 14 | EC1300 | EC1170 | 2011-04-22 15:24 | 2011-05-13 09:36 |  |  | Project Controls, Project Controls | Active | 0 | 3168 | 0 | 218 | -1144 | 0 | 3168 | N
EC1300 | Not Started | EC00515.Int-Finish.Coverings | Award Contract for Flooring | 5 | EC1310, EC1300 | EC1250, EC1080 | 2011-05-13 09:36 | 2011-05-19 17:00 |  |  | Project Controls, Project Controls | Active | 0 | 1056 | 0 | 218 | 0 | 0 | 1056 | N
EC1190 | In Progress | EC00515.Mechanicals.HVAC | Prepare and Solicit Bids for Heat Pump | 14 | EC1240 | EC1160 | 2011-03-31 08:00 | 2011-04-20 11:12 | 2011-04-14 13:05 |  | Project Controls, Project Controls | Active | 92 | 3168 | 8243.12 | -13 | -253.44 | -5328.56 | 716.79 | Y
EC1240 | Not Started | EC00515.Mechanicals.HVAC | Review Bids for Heat Pump | 10 | EC1270 | EC1190 | 2011-04-20 11:12 | 2011-05-03 17:00 |  |  | Project Controls, Project Controls | Active | 0 | 2112 | 0 | -13 | -1672 | 0 | 2112 | Y
EC1270 | Not Started | EC00515.Mechanicals.HVAC | Award Contract for Heat Pump | 6 | EC1290 | EC1240 | 2011-05-04 08:00 | 2011-05-11 17:00 |  |  |  | Active | 0 | 0 | 0 | -13 | 0 | 0 | 0 | Y
EC1180 | Completed | EC00515.Ex-Finish.Brick | Prepare and Solicit Bids for Brick Exterior | 14 | EC1220 | EC1070 | 2011-03-21 15:24 | 2011-04-11 09:36 | 2011-03-18 15:00 | 2011-04-13 09:12 | Project Controls, Project Controls | Active | 100 | 3168 | 11385 |  | 0 | -8217 | 0 | N
EC1220 | Completed | EC00515.Ex-Finish.Brick | Review Bids for Brick | 14 | EC1260 | EC1180 | 2011-04-11 09:36 | 2011-04-29 13:48 | 2011-04-08 09:12 | 2011-04-28 13:24 | Project Controls, Project Controls | Active | 100 | 3168 | 10560 |  | 0 | -7392 | 0 | N
EC1260 | In Progress | EC00515.Ex-Finish.Brick | Award Contract for Brick | 5 | EC1280 | EC1220 | 2011-04-29 13:48 | 2011-05-06 11:12 | 2011-04-21 13:24 |  | Project Controls, Project Controls | Active | 8 | 1056 | 330 | 364 | -3.52 | -245.52 | 3795 | N
EC1040 | Completed | EC00515.Ex-Finish.Brick | Assemble Brick Samples | 0 | EC1070 | EC1030 | 2011-02-15 15:24 |  | 2011-02-17 08:00 |  |  | Active | 0 | 0 | 0 |  | 0 | 0 | 0 | N
EC1050 | Completed | EC00515.D&E | Assemble Technical Data for Heat Pump | 7 | EC1160 | EC1030 | 2011-02-15 15:24 | 2011-02-24 17:00 | 2011-02-16 08:00 | 2011-02-25 09:36 | Paul Kim | Active | 100 | 3456 | 3900 |  | 0 | -444 | 0 | N
EC1160 | Completed | EC00515.D&E | Review Technical Data on Heat Pumps | 24 | EC1190 | EC1050 | 2011-02-25 08:00 | 2011-03-30 17:00 | 2011-02-24 09:36 | 2011-04-06 09:36 | Paul Kim | Active | 100 | 11520 | 12300 |  | 0 | -780 | 0 | N
EC1060 | Completed | EC00515.Int-Finish.Coverings | Assemble and Submit Flooring Samples | 0 | EC1080 | EC1030 | 2011-02-15 15:24 |  | 2011-02-25 08:00 |  |  | Active | 0 | 0 | 0 |  | 0 | 0 | 0 | N
EC1030 | Completed | EC00515.D&E | Review and Approve Designs | 22 | EC1040, EC1050, EC1060, EC1090 | EC1000 | 2011-01-17 09:36 | 2011-02-15 15:24 | 2011-01-17 09:36 | 2011-02-17 15:24 | Paul Kim | Active | 100 | 10368 | 11820 |  | 0 | -1452 | 0 | N
EC1070 | Completed | EC00515.Ex-Finish.Brick | Review and Approve Brick Samples | 24 | EC1180 | EC1040 | 2011-02-15 15:24 | 2011-03-21 15:24 | 2011-02-28 08:00 | 2011-04-13 08:00 | Paul Kim | Active | 100 | 11520 | 15900 |  | 0 | -4380 | 0 | N
EC1290 | Not Started | EC00515.Mechanicals.HVAC | Fabricate and Deliver Heat Pump and Controls | 422 | EC1650 | EC1270 | 2011-05-12 08:00 | 2012-12-24 11:12 |  |  | Project Controls, Project Controls | Active | 0 | 92928 | 0 | -13 | 0 | 0 | 92928 | Y
EC1080 | Completed | EC00515.Int-Finish.Coverings | Review and Approve Flooring | 24 | EC1170 | EC1060 | 2011-02-15 15:24 | 2011-03-21 15:24 | 2011-02-25 08:00 | 2011-04-11 17:00 | Paul Kim | Active | 100 | 11520 | 14760 |  | 0 | -3240 | 0 | N
EC1280 | Not Started | EC00515.Ex-Finish.Brick | Deliver Brick | 1 | EC1550 | EC1260 | 2011-05-06 11:12 | 2011-05-09 11:12 |  |  |  | Active | 0 | 0 | 0 | 364 | 0 | 0 | 0 | N
EC1310 | Not Started | EC00515.Int-Finish.Coverings | Fabricate and Deliver Flooring | 278 | EC1790 | EC1300 | 2011-05-20 08:00 | 2012-06-13 11:12 |  |  | Project Controls, Project Controls | Active | 0 | 61248 | 0 | 218 | 0 | 0 | 61248 | N
EC1090 | Completed | EC00515.Found | Begin Building Construction | 0 | EC1100 | EC1030, EC1090 | 2011-02-15 15:24 |  | 2011-02-28 08:00 |  |  | Active | 0 | 0 | 0 |  | 0 | 0 | 0 | N
EC1100 | Completed | EC00515.Found | Site Preparation | 43 | EC1230 | EC1090 | 2011-02-15 15:24 | 2011-04-15 17:00 | 2011-02-23 08:00 | 2011-04-18 09:36 | Excavator | Active | 100 | 24192 | 21350 |  | 0 | 2842 | 0 | N
EC1230 | Not Started | EC00515.Found | Excavation | 24 | EC1320, EC1330 | EC1100 | 2011-04-18 08:00 | 2011-05-19 17:00 |  |  | Excavator, Excavator | Active | 0 | 13440 | 0 | 113 | -5600 | 0 | 13440 | N
EC1320 | Not Started | EC00515.Found | Install Underground Water Lines | 12 | EC1340 | EC1230 | 2011-05-20 08:00 | 2011-06-06 17:00 |  |  | Plumber, Plumber | Active | 0 | 5280 | 0 | 113 | 0 | 0 | 5280 | N
EC1330 | Not Started | EC00515.Found | Install Underground Electric Conduit | 12 | EC1340 | EC1230 | 2011-05-20 08:00 | 2011-06-06 17:00 |  |  | Electrician, Electrician | Active | 0 | 9120 | 0 | 113 | 0 | 0 | 9120 | N
EC1340 | Not Started | EC00515.Found | Form/Pour Concrete Footings | 24 | EC1350 | EC1320, EC1330 | 2011-06-07 08:00 | 2011-07-08 17:00 |  |  | Ironworker, Rough Carpenter, Operator, Ironworker, Rough Carpenter, Operator | Active | 0 | 31520 | 0 | 113 | 0 | 0 | 31520 | N
EC1350 | Not Started | EC00515.Found | Concrete Foundation Walls | 24 | EC1360 | EC1340 | 2011-07-11 08:00 | 2011-08-11 17:00 |  |  | Ironworker, Laborer-Construction, Rough Carpenter, Ironworker, Laborer-Construction, Rough Carpenter | Active | 0 | 26720 | 0 | 113 | 0 | 0 | 26720 | N
EC1360 | Not Started | EC00515.Found | Form and Pour Slab | 12 | EC1370, EC1390 | EC1350, EC1380 | 2011-08-12 08:00 | 2011-08-29 17:00 |  |  | Finish Carpenter, Ironworker, Rough Carpenter, Laborer-Construction, Finish Carpenter, Ironworker, Rough Carpenter, Laborer-Construction | Active | 0 | 19792 | 0 | 113 | 0 | 0 | 19792 | N
EC1370 | Not Started | EC00515.Found | Backfill and Compact Walls | 5 | EC1380, EC1390 | EC1360 | 2011-08-30 08:00 | 2011-09-05 15:24 |  |  | Excavator, Finish Carpenter, Excavator, Finish Carpenter | Active | 0 | 5260.8 | 0 | 113 | 0 | 0 | 5260.8 | N
EC1380 | Not Started | EC00515.Found | Foundation Phase Complete | 0 | EC1090 | EC1370 |  | 2011-09-05 15:24 |  |  |  | Active | 0 | 0 | 0 | 164 | 0 | 0 | 0 | N
EC1410 | Not Started | EC00515.Structure | Begin Structural Phase | 0 |  | EC1390 | 2011-11-10 15:24 |  |  |  |  | Active | 0 | 0 | 0 | 418 | 0 | 0 | 0 | N
EC1390 | Not Started | EC00515.Structure | Erect Structural Frame | 48 | EC1410, EC1420 | EC1370 | 2011-09-05 15:24 | 2011-11-10 15:24 |  |  | Ironworker, Ironworker | Active | 0 | 22720 | 0 | 113 | 0 | 0 | 22720 | N
EC1420 | Not Started | EC00515.Structure | Floor Decking | 34 | EC1430 | EC1390 | 2011-11-10 15:24 | 2011-12-28 11:12 |  |  | Ironworker, Ironworker, Ironworker | Active | 0 | 15904 | 0 | 113 | 0 | 0 | 15904 | N
EC1460 | Not Started | EC00515.Structure | Erect Stairwell and Elevator Walls | 24 | EC1540, EC1520 | EC1430 | 2012-02-16 11:12 | 2012-03-21 11:12 |  |  | Laborer-Construction | Active | 0 | 6720 | 0 | 125 | 0 | 0 | 6720 | N
EC1430 | Not Started | EC00515.Structure | Concrete First Floor | 36 | EC1460, EC1470, EC1440, EC1480 | EC1420 | 2011-12-28 11:12 | 2012-02-16 11:12 |  |  | Ironworker, Laborer-Construction, Rough Carpenter, Finish Carpenter | Active | 0 | 30288 | 0 | 113 | 0 | 0 | 30288 | N
EC1470 | Not Started | EC00515.Structure | Concrete Basement Slab | 24 | EC1540 | EC1430 | 2012-02-16 11:12 | 2012-03-21 11:12 |  |  | Ironworker, Laborer-Construction, Laborer-Construction, Rough Carpenter, Finish Carpenter | Active | 0 | 47104 | 0 | 125 | 0 | 0 | 47104 | N
EC1540 | Not Started | EC00515.Structure | Structure Complete | 0 | EC1550, EC1420 | EC1460, EC1470, EC1480 |  | 2012-04-06 11:12 |  |  |  | Active | 0 | 0 | 0 | 113 | 0 | 0 | 0 | N
EC1590 | Not Started | EC00515.Ex-Finish | Close-In Phase Begins | 0 |  | EC1550 | 2012-05-01 09:36 |  |  |  |  | Active | 0 | 0 | 0 | 295 | 0 | 0 | 0 | N
EC1550 | Not Started | EC00515.Ex-Finish.Brick | Brick Exterior Walls | 17 | EC1590, EC1560, EC1600 | EC1280, EC1540 | 2012-04-06 11:12 | 2012-05-01 09:36 |  |  | Laborer-Construction, Laborer-Construction | Active | 0 | 11424 | 0 | 113 | 0 | 0 | 11424 | N
EC1560 | Not Started | EC00515.Ex-Finish.Win | Install Door and Window Frames | 2 | EC1580 | EC1550 | 2012-04-13 11:12 | 2012-04-17 15:24 |  |  | Finish Carpenter, Finish Carpenter | Active | 0 | 1286.4 | 0 | 141 | 0 | 0 | 1286.4 | N
EC1600 | Not Started | EC00515.Ex-Finish.Roof | Insulation and Built-up Roofing | 24 | EC1620 | EC1550, EC1580 | 2012-05-01 09:36 | 2012-06-04 09:36 |  |  | Laborer-Construction, Laborer-Construction | Active | 0 | 7520 | 0 | 113 | 0 | 0 | 7520 | N
EC1580 | Not Started | EC00515.Ex-Finish.Win | Install Exterior Doors and Windows | 5 | EC1600, EC1620 | EC1560 | 2012-04-17 15:24 | 2012-04-24 13:48 |  |  | Finish Carpenter, Finish Carpenter | Active | 0 | 2572.8 | 0 | 141 | 0 | 0 | 2572.8 | N
EC1620 | Not Started | EC00515.Ex-Finish | Building Enclosed | 0 | EC1630, EC1650, EC1640, EC1700, EC1710 | EC1600, EC1580 |  | 2012-06-04 09:36 |  |  |  | Active | 0 | 0 | 0 | 113 | 0 | 0 | 0 | N
EC1490 | Not Started | EC00515.Mechanicals | Rough-In Phase Begins | 0 | EC1680, EC1520 | EC1440 | 2012-02-27 11:12 |  |  |  |  | Active | 0 | 0 | 0 | 220 | 0 | 0 | 0 | N
EC1440 | Not Started | EC00515.Mechanicals.Systems | Set Mechanical and Electrical Equipment | 36 | EC1490, EC1500 | EC1430 | 2012-01-06 11:12 | 2012-02-27 11:12 |  |  | Operator | Active | 0 | 17280 | 0 | 172 | 0 | 0 | 17280 | N
EC1500 | Not Started | EC00515.Mechanicals.HVAC | Install HVAC Ducts | 24 | EC1630, EC1510 | EC1440 | 2012-02-27 11:12 | 2012-03-30 11:12 |  |  | HVAC, HVAC | Active | 0 | 8448 | 0 | 172 | 0 | 0 | 8448 | N
EC1630 | Not Started | EC00515.Mechanicals.HVAC | Insulate Ducts | 5 | EC1650 | EC1620, EC1500 | 2012-06-04 09:36 | 2012-06-08 17:00 |  |  | HVAC, HVAC | Active | 0 | 1689.6 | 0 | 126 | 0 | 0 | 1689.6 | N
EC1650 | Not Started | EC00515.Mechanicals.HVAC | Set Heat Pump | 12 | EC1660, EC1670 | EC1290, EC1620, EC1630 | 2012-12-24 11:12 | 2013-01-09 11:12 |  |  | Operator | Active | 0 | 5760 | 0 | -13 | 0 | 0 | 5760 | Y
EC1510 | Not Started | EC00515.Mechanicals.Systems | Rough-In Plumbing/Piping | 2 | EC1640, EC1490 | EC1500, EC1660 | 2012-03-02 11:12 | 2012-03-06 15:24 |  |  | Plumber, Plumber | Active | 0 | 7976 | 0 | 67 | 0 | 0 | 7976 | N
EC1640 | Not Started | EC00515.Mechanicals.Systems | Install Wiring and Cable | 36 | EC1660 | EC1620, EC1510 | 2012-06-04 09:36 | 2012-07-24 09:36 |  |  | Electrician, Electrician | Active | 0 | 27360 | 0 | 67 | 0 | 0 | 27360 | N
EC1520 | Not Started | EC00515.Mechanicals.Lifts | Install Elevator Rails and Equipment | 2 | EC1690 | EC1460, EC1490 | 2012-03-21 11:12 | 2012-03-23 15:24 |  |  | Elevator Installer, Elevator Installer | Active | 0 | 2016 | 0 | 203 | 0 | 0 | 2016 | N
EC1660 | Not Started | EC00515.Mechanicals.Systems | Connect Equipment | 1 | EC1680 | EC1650, EC1640 | 2013-01-09 11:12 | 2013-01-10 11:12 |  |  |  | Active | 0 | 0 | 0 | -7 | 0 | 0 | 0 | Y
EC1680 | Not Started | EC00515.Mechanicals.HVAC | Startup and Test HVAC | 2 | EC1690 | EC1660, EC1670, EC1490 | 2013-01-18 13:48 | 2013-01-22 17:00 |  |  | Operator | Active | 0 | 1152 | 0 | -13 | 0 | 0 | 1152 | Y
EC1690 | Not Started | EC00515.Mechanicals | Rough In Complete | 0 | EC1700, EC1710 | EC1520, EC1680 |  | 2013-01-22 17:00 |  |  |  | Active | 0 | 0 | 0 | -13 | 0 | 0 | 0 | Y
EC1700 | Not Started | EC00515.Int-Finish | Drywall in Offices | 36 | EC1740, EC1720 | EC1620, EC1690 | 2013-01-23 08:00 | 2013-03-13 17:00 |  |  | Finish Carpenter | Active | 0 | 19296 | 0 | -13 | 0 | 0 | 19296 | Y
EC1740 | Not Started | EC00515.Int-Finish.Carp | Install Ceiling Grid | 36 | EC1760, EC1770, EC1790 | EC1700 | 2013-03-14 08:00 | 2013-05-02 17:00 |  |  | Finish Carpenter | Active | 0 | 28456 | 0 | -13 | 0 | 0 | 28456 | Y
EC1760 | Not Started | EC00515.Int-Finish.Fixtures | Install Lighting Fixtures | 7 | EC1790 | EC1740 | 2013-03-26 08:00 | 2013-04-04 09:36 |  |  | Electrician | Active | 0 | 11232 | 0 | 7 | 0 | 0 | 11232 | N
EC1770 | Not Started | EC00515.Mechanicals.HVAC | Install AC Grills and Registers | 5 | EC1790 | EC1740 | 2013-03-26 08:00 | 2013-04-01 17:00 |  |  |  | Active | 0 | 0 | 0 | 10 | 0 | 0 | 0 | N
EC1790 | Not Started | EC00515.Int-Finish.Coverings | Install Floor and Carpeting | 12 | EC1800, EC1810 | EC1310, EC1740, EC1760, EC1770 | 2013-05-03 08:00 | 2013-05-20 17:00 |  |  | Floor and Carpet Layer | Active | 0 | 4320 | 0 | -13 | 0 | 0 | 4320 | Y
EC1800 | Not Started | EC00515.Int-Finish.Carp | Finish Carpentry and Millwork | 12 | EC1820 | EC1790, EC1800 | 2013-05-21 08:00 | 2013-06-05 17:00 |  |  | Finish Carpenter | Active | 0 | 6432 | 0 | -13 | 0 | 0 | 6432 | Y
EC1810 | Not Started | EC00515.Int-Finish.Fixtures | Install Plumbing Fixtures | 5 | EC1820 | EC1790 | 2013-05-21 08:00 | 2013-05-27 15:24 |  |  | Plumber | Active | 0 | 2112 | 0 | -6 | 0 | 0 | 2112 | Y
EC1710 | Not Started | EC00515.Mechanicals.Lifts | Install Elevator Cab and Finishes | 5 | EC1820 | EC1620, EC1690 | 2013-01-23 08:00 | 2013-01-29 15:24 |  |  | Elevator Installer | Active | 0 | 4032 | 0 | 78 | 0 | 0 | 4032 | N
EC1720 | Not Started | EC00515.Int-Finish.Paint | Paint Building Interior | 12 | EC1820 | EC1700 | 2013-02-01 08:00 | 2013-02-18 17:00 |  |  | Painter | Active | 0 | 6720 | 0 | 64 | 0 | 0 | 6720 | N
EC1820 | Not Started | EC00515.Int-Finish | Touch-up and Clean-up | 2 | EC1830 | EC1800, EC1810, EC1710, EC1720 | 2013-06-06 08:00 | 2013-06-10 11:12 |  |  | Finish Carpenter, Laborer-Construction, Painter | Active | 0 | 2406.4 | 0 | -13 | 0 | 0 | 2406.4 | Y
EC1830 | Not Started | EC00515.Mechanicals.HVAC | Test and Balance HVAC Equipment | 2 | EC1840 | EC1820 | 2013-06-10 11:12 | 2013-06-12 15:24 |  |  | Operator, Operator | Active | 0 | 1152 | 0 | -13 | 0 | 0 | 1152 | Y
EC1840 | Not Started | EC00515.Int-Finish | Finishes Complete | 0 | EC1850, EC1700 | EC1830 |  | 2013-06-12 15:24 |  |  |  | Active | 0 | 0 | 0 | -13 | 0 | 0 | 0 | Y
EC1850 | Not Started | EC00515.Int-Finish | Punch List | 5 | EC1860 | EC1840 | 2013-06-12 15:24 | 2013-06-19 13:48 |  |  | Painter, Finish Carpenter, Laborer-Construction | Active | 0 | 4812.8 | 0 | 0 | 0 | 0 | 4812.8 | Y
EC1860 | Not Started | EC00515.Int-Finish | Building Addition Complete | 0 |  | EC1850 |  | 2013-06-19 13:48 |  |  |  | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y
EC1480 | Not Started | EC00515.Structure | Concrete Second Floor | 36 | EC1540 | EC1430, EC1540 | 2012-02-16 11:12 | 2012-04-06 11:12 |  |  | Ironworker, Laborer-Construction, Rough Carpenter, Finish Carpenter | Active | 0 | 30288 | 0 | 113 | 0 | 0 | 30288 | N
EC1670 | Not Started | EC00515.Mechanicals.HVAC | Relocate HVAC Chiller | 7 | EC1680 | EC1650 | 2013-01-09 11:12 | 2013-01-18 13:48 |  |  | Operator, Electrician, HVAC | Active | 0 | 9158.4 | 0 | -13 | 0 | 0 | 9158.4 | Y
EC1010 | Completed | EC00515.D&E | Start Office Building Addition Project | 0 | EC1000 |  | 2010-11-01 08:00 |  | 2010-11-01 08:00 |  |  | Active | 0 | 0 | 0 |  | 0 | 0 | 0 | N

## RSRC
rsrc_short_name | rsrc_name | rsrc_title_name
Resource ID | Resource Name | Title
MathisL | Lane Mathis, CIO
AndersonG | Glen Anderson, VP Development
VincentI | Ian Vincent
CharlesM | Mandy Charles, VP IT Ops
ZhuS | Shannon Zhu
LaffertyV | Vanessa Lafferty
BennettC | Carina Bennett
PaxsonD | Dan Paxson
SinghD | Deepak Singh
SharpeD | Dan Sharpe
ITCon | IT Consultant
LiR | Roy Li
RiceB | Barbara Rice, PMO Director
ChopraA | Amit Chopra
AbrahamM | Molly Abraham
WrenJ | Jo Wren
ATM ENG | Automation Systems Engineer
IT | Information Technology Group
Product Dev | Product Development Resources
ManufEng | Manufacturing Engineering Group
CaseyA | Andrea Casey | Six Sigma Engineer
RileyP | Paul Riley | Product Engineer
MarshallG | Gary Marshall | Product Engineer
LeeC | Cindy Lee | Product Engineering Specialist
ProductOps | Product Operations Group
HillF | Frank Hill
WestL | Larry West
BaxterS | Sue Baxter
WynnA | Alice Wynn
ProductMktg | Product Marketing Group
LincolnR | Robert Lincoln | Manufacturing Engineer
ShawH | Harry Shaw | Senior Engineering Lead
JacksonL | Lendell Jackson
RickelsS | Sam Rickels
IthanP | Peg Ithan
Corporate | Corporate Resources
Bpmpmo | Business Process PMO
JohnsonR | Rea Johnson
McneillL | Lori McNeil
Operations | Process Operations
BillingsJ | Judy Billings
Chuf | Frank Chu
Contr | External Contractors
Bpm001 | BPM Consultant 1
Bpm002 | BPM Consultant 2
Bpm003 | BPM Consultant 3
FrostB | Ben Frost
CooperP | Peter Cooper
PetersonM | Michelle Peterson
PrescottW | Wayne Prescott
E&C Resources | E&C Resources
Subcontractors | Subcontractor
Trades | Trades
Management | Management
Purchasing | Purchasing Department
Engineering | Engineering Department
Cretefinisher | Concrete Finisher
Admin | Administrator
Fabrication | Fabrication
Elev Inst | Elevator Installer
Elec | Electrician
Floor | Floor and Carpet Layer
Operator | Operator
Plumb | Plumber
FCarp | Finish Carpenter
RCarp | Rough Carpenter
GenLabor | Laborer-Construction
FieldEng | Field Engineer
IrnWrk | Ironworker
FieldEngSnr | Field Eng-Senior
FieldEngAsst | Field Eng-Assistant
Exc | Excavator
KimP | Paul Kim | Design Engineer
YoungJ | Jeff Young | Analyst
PMs | Project Managers
ResnerW | Wendy Resner | Automation Systems Engineer
DesEng | Design Engineer
McGuireO | Owen McGuire, Project Manager
Project Controls | Project Controls | Accounts Manager
InsEng | Instrumentation Engineer
HVAC | HVAC
Millwork Carpentry | Millwork Subcontractor
Thermal Protection | Thermal Protection Subcontractor
Finishes | Finishes & Fit-out Subcontractor
Concrete-Sub | Concrete Foundation Subcontractor
Specialty Metals | Specialty Metal Fabricator Subcontractor
Pools | Pool Installation Subcontractor
Conveying-Sub | Conveying Subcontractor
Fire Suppression | Fire Suppression Subcontractor
Landscaping | Landscaping Subcontractor
Specialties | FF&E Specialties
Drywall | Drywall Subcontractor
Roofing | Roofing Subcontractor
Glass | Glass & Glazing Subcontractor
Paving | Paving & Roadways Subcontractor
Utilities | Utilities Subcontractor
OPTGP | Operations Test Group
INSP | Inspections | Senior Inspector
Hydro | Hydroblaster
Paint | Painter
Material | Material Resources
Test resource | New Resource Name
Test Resource Child | New Resource Name-1

## TASKRSRC
rsrc_id | task_id | TASK__status_code | role_id | acct_id | rsrc_type | start_date | end_date | delete_record_flag
Resource ID | Activity ID | (*)Activity Status | Role ID | Cost Account ID | (*)Resource Type | (*)Start | (*)Finish | Delete This Row
KimP | EC1030 | Completed |  | 00800 | Labor | 2011-01-17 09:36 | 2011-02-17 15:24
KimP | EC1000 | Completed |  | 00800 | Labor | 2010-11-01 08:00 | 2011-01-19 09:36
KimP | EC1050 | Completed |  | 00800 | Labor | 2011-02-16 08:00 | 2011-02-25 09:36
KimP | EC1160 | Completed |  | 00800 | Labor | 2011-02-24 09:36 | 2011-04-06 09:36
Exc | EC1100 | Completed | E&C.Civil/Structural | 00800 | Labor | 2011-02-23 08:00 | 2011-04-18 09:36
Exc | EC1230 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-05-02 08:00 | 2011-06-03 17:00
Plumb | EC1320 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-06 09:00 | 2011-06-22 09:00
Elec | EC1330 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-06 09:00 | 2011-06-22 09:00
IrnWrk | EC1340 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-22 10:00 | 2011-07-27 10:00
RCarp | EC1340 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-22 10:00 | 2011-07-27 10:00
Operator | EC1340 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-22 10:00 | 2011-07-27 10:00
IrnWrk | EC1350 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-07-27 11:00 | 2011-08-30 11:00
GenLabor | EC1350 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-07-27 11:00 | 2011-08-30 11:00
RCarp | EC1350 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-07-27 11:00 | 2011-08-30 11:00
FCarp | EC1360 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-08-30 13:00 | 2011-09-16 12:00
IrnWrk | EC1360 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-08-30 13:00 | 2011-09-16 12:00
RCarp | EC1360 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-08-30 13:00 | 2011-09-16 12:00
GenLabor | EC1360 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-08-30 13:00 | 2011-09-16 12:00
Exc | EC1370 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-09-16 14:00 | 2011-09-23 11:24
FCarp | EC1370 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-09-16 14:00 | 2011-09-23 11:24
IrnWrk | EC1390 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-09-23 13:24 | 2011-12-01 13:24
IrnWrk | EC1420 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-12-01 14:24 | 2012-01-20 10:12
IrnWrk | EC1430 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-01-20 10:12 | 2012-03-12 10:12
GenLabor | EC1430 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-01-20 10:12 | 2012-03-12 10:12
RCarp | EC1430 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-01-20 10:12 | 2012-03-12 10:12
FCarp | EC1430 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-01-20 10:12 | 2012-03-12 10:12
GenLabor | EC1460 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-04-13 10:12
IrnWrk | EC1470 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-04-13 10:12
GenLabor | EC1470 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-04-13 10:12
GenLabor | EC1470 | Not Started | E&C.Civil/Structural |  | Labor | 2012-03-12 10:12 | 2012-04-13 10:12
RCarp | EC1470 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-04-13 10:12
FCarp | EC1470 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-04-13 10:12
Elev Inst | EC1520 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-04-13 10:12 | 2012-04-17 14:24
Elev Inst | EC1710 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-02-21 15:43 | 2013-02-28 14:07
Project Controls | EC1190 | In Progress | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-04-14 13:05 | 2011-05-03 16:17
Project Controls | EC1240 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-05-04 08:12 | 2011-05-17 14:00
Project Controls | EC1290 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-05-25 14:43 | 2013-01-23 08:55
HVAC | EC1500 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-21 10:12 | 2012-04-24 10:12
HVAC | EC1630 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-06-28 10:24 | 2012-07-06 08:48
Operator | EC1650 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-01-23 09:55 | 2013-02-08 09:55
Operator | EC1680 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-02-19 11:31 | 2013-02-21 15:43
Operator | EC1830 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-07-12 09:55 | 2013-07-16 14:07
Operator | EC1440 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-01-31 10:12 | 2012-03-21 10:12
Plumb | EC1510 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-08-24 15:11 | 2012-08-29 09:23
Elec | EC1640 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-08-31 15:11 | 2012-10-23 15:11
KimP | EC1070 | Completed |  | 00800 | Labor | 2011-02-28 08:00 | 2011-04-13 08:00
Project Controls | EC1180 | Completed | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-03-18 15:00 | 2011-04-13 09:12
Project Controls | EC1220 | Completed | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-04-08 09:12 | 2011-04-28 13:24
Project Controls | EC1260 | In Progress | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-04-21 13:24 | 2011-05-05 10:48
GenLabor | EC1550 | Not Started | E&C.Civil/Structural |  | Labor | 2012-05-01 10:12 | 2012-05-24 08:36
GenLabor | EC1600 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-05-24 09:24 | 2012-06-28 09:24
FCarp | EC1560 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-05-08 10:12 | 2012-05-10 14:24
FCarp | EC1580 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-05-10 15:12 | 2012-05-17 13:36
FCarp | EC1700 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-02-21 15:43 | 2013-04-12 15:43
FCarp | EC1820 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-07-09 15:43 | 2013-07-12 09:55
GenLabor | EC1820 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-07-09 15:43 | 2013-07-12 09:55
Paint | EC1820 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-07-09 15:43 | 2013-07-10 14:07
Paint | EC1850 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-07-16 14:07 | 2013-07-18 09:55
FCarp | EC1850 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-07-16 14:07 | 2013-07-23 11:31
GenLabor | EC1850 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-07-16 14:07 | 2013-07-23 11:31
Elec | EC1760 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-04-24 15:43 | 2013-05-06 08:19
Plumb | EC1810 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-06-20 15:43 | 2013-06-27 14:07
KimP | EC1080 | Completed |  | 00800 | Labor | 2011-02-25 08:00 | 2011-04-11 17:00
Project Controls | EC1170 | In Progress | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-04-04 15:38 | 2011-05-06 15:38
Project Controls | EC1250 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-05-06 16:38 | 2011-05-27 10:50
Project Controls | EC1300 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-05-27 11:50 | 2011-06-06 10:14
Project Controls | EC1310 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-06-06 11:14 | 2012-07-09 15:26
Floor | EC1790 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-06-04 15:43 | 2013-06-20 15:43
FCarp | EC1740 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-04-12 15:43 | 2013-06-04 15:43
FCarp | EC1800 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-06-20 15:43 | 2013-07-09 15:43
Paint | EC1720 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-03-04 15:43 | 2013-03-20 15:43
IrnWrk | EC1480 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-05-01 10:12
GenLabor | EC1480 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-05-01 10:12
RCarp | EC1480 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-05-01 10:12
FCarp | EC1480 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-12 10:12 | 2012-05-01 10:12
Operator | EC1670 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-02-08 09:55 | 2013-02-19 11:31
Elec | EC1670 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-02-08 09:55 | 2013-02-19 11:31
HVAC | EC1670 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-02-08 09:55 | 2013-02-19 11:31
| EC1510 | Not Started | E&C.Engr.ME | 00800 | Labor | 2012-08-24 15:11 | 2012-08-29 09:23
| EC1760 | Not Started | E&C.Engr.EE | 00800 | Labor | 2013-04-24 15:43 | 2013-05-06 08:19
GenLabor | EC1550 | Not Started | E&C.Civil/Structural |  | Labor | 2012-05-01 11:00 | 2012-05-24 09:24
FCarp | EC1560 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-05-08 11:00 | 2012-05-10 15:12
IrnWrk | EC1420 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-12-01 14:24 | 2012-01-20 10:12
Operator | EC1830 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2013-07-12 09:55 | 2013-07-16 14:07
HVAC | EC1630 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-06-28 11:24 | 2012-07-06 09:48
HVAC | EC1500 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-03-21 11:00 | 2012-04-24 11:00
GenLabor | EC1600 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-05-24 10:24 | 2012-06-28 10:24
FCarp | EC1580 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-05-10 16:12 | 2012-05-17 14:36
Elev Inst | EC1520 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-04-13 11:00 | 2012-04-17 15:12
Elec | EC1640 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-08-31 16:11 | 2012-10-23 16:11
Plumb | EC1510 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2012-08-24 16:11 | 2012-08-29 10:23
| EC1510 | Not Started | E&C.Engr.ME | 00800 | Labor | 2012-08-24 16:11 | 2012-08-29 10:23
Project Controls | EC1190 | In Progress | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-04-14 13:05 | 2011-05-04 08:12
Project Controls | EC1240 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-05-04 08:55 | 2011-05-17 14:43
Project Controls | EC1180 | Completed | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-03-18 15:00 | 2011-04-13 09:12
KimP | EC1000 | Completed |  | 00800 | Labor | 2010-11-01 08:00 | 2011-01-19 09:36
Project Controls | EC1170 | In Progress | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-04-04 15:38 | 2011-05-06 16:38
Project Controls | EC1250 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-05-09 08:38 | 2011-05-27 11:50
Project Controls | EC1300 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-05-27 13:50 | 2011-06-06 11:14
Project Controls | EC1220 | Completed | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-04-08 09:12 | 2011-04-28 13:24
Project Controls | EC1260 | In Progress | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-04-21 13:24 | 2011-05-05 11:24
Plumb | EC1320 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-06 10:00 | 2011-06-22 10:00
Exc | EC1230 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-05-02 09:00 | 2011-06-06 09:00
Project Controls | EC1290 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-05-25 15:43 | 2013-01-23 09:55
Project Controls | EC1310 | Not Started | E&C.E&C Shared.Accounting | 00800 | Labor | 2011-06-06 13:14 | 2012-07-09 16:26
Exc | EC1370 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-09-16 15:00 | 2011-09-23 13:24
FCarp | EC1370 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-09-16 15:00 | 2011-09-23 13:24
IrnWrk | EC1390 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-09-23 14:24 | 2011-12-01 14:24
IrnWrk | EC1340 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-22 11:00 | 2011-07-27 11:00
RCarp | EC1340 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-22 11:00 | 2011-07-27 11:00
Operator | EC1340 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-22 11:00 | 2011-07-27 11:00
Elec | EC1330 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-06-06 10:00 | 2011-06-22 10:00
FCarp | EC1360 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-08-30 14:00 | 2011-09-16 14:00
IrnWrk | EC1360 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-08-30 14:00 | 2011-09-16 14:00
RCarp | EC1360 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-08-30 14:00 | 2011-09-16 14:00
GenLabor | EC1360 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-08-30 14:00 | 2011-09-16 14:00
IrnWrk | EC1350 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-07-27 13:00 | 2011-08-30 12:00
GenLabor | EC1350 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-07-27 13:00 | 2011-08-30 12:00
RCarp | EC1350 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-07-27 13:00 | 2011-08-30 12:00
IrnWrk | EC1420 | Not Started | E&C.Civil/Structural | 00800 | Labor | 2011-12-01 14:24 | 2012-01-20 10:12

## PROJCOST
task_id | cost_name | TASK__status_code | target_cost | act_cost | remain_cost | total_cost | delete_record_flag
Activity ID | Expense Item | (*)Activity Status | Budgeted Cost($) | Actual Cost($) | Remaining Cost($) | At Completion Cost($) | Delete This Row
EC1340 | Crane | Not Started | 800 | 0 | 800 | 800
EC1350 | Crane | Not Started | 800 | 0 | 800 | 800
EC1360 | Crane | Not Started | 400 | 0 | 400 | 400
EC1390 | Crane | Not Started | 1600 | 0 | 1600 | 1600
EC1420 | Crane | Not Started | 1120 | 0 | 1120 | 1120
EC1430 | Crane | Not Started | 1200 | 0 | 1200 | 1200
EC1470 | Crane | Not Started | 1600 | 0 | 1600 | 1600
EC1550 | Crane | Not Started | 6720 | 0 | 6720 | 6720
EC1600 | Crane | Not Started | 800 | 0 | 800 | 800
EC1510 | Piping Material | Not Started | 5000 | 0 | 5000 | 5000
EC1480 | Crane | Not Started | 1200 | 0 | 1200 | 1200
EC1740 | Ceiling Tile | Not Started | 6620 | 0 | 6620 | 6620
EC1740 | Ceiling TIle Spec Change | Not Started | 2540 | 0 | 2540 | 2540

## TASKPRED
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | lag_hr_cnt | predtask__rsrc_id | task__rsrc_id | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Lag(h) | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Delete This Row
EC1080 | EC1170 | FS | Completed | In Progress | EC00515 | EC00515 | EC00515.Int-Finish.Coverings Floor and Carpeting | EC00515.Int-Finish.Coverings Floor and Carpeting | Review and Approve Flooring | Prepare and Solicit Bids for Flooring | 0 | KimP | Project Controls
EC1170 | EC1250 | FS | In Progress | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Coverings Floor and Carpeting | EC00515.Int-Finish.Coverings Floor and Carpeting | Prepare and Solicit Bids for Flooring | Review Bids for Flooring | 0 | Project Controls | Project Controls
EC1250 | EC1300 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Coverings Floor and Carpeting | EC00515.Int-Finish.Coverings Floor and Carpeting | Review Bids for Flooring | Award Contract for Flooring | 0 | Project Controls | Project Controls
EC1160 | EC1190 | FS | Completed | In Progress | EC00515 | EC00515 | EC00515.D&E Design and Engineering | EC00515.Mechanicals.HVAC HVAC | Review Technical Data on Heat Pumps | Prepare and Solicit Bids for Heat Pump | 0 | KimP | Project Controls
EC1190 | EC1240 | FS | In Progress | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.HVAC HVAC | Prepare and Solicit Bids for Heat Pump | Review Bids for Heat Pump | 0 | Project Controls | Project Controls
EC1240 | EC1270 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.HVAC HVAC | Review Bids for Heat Pump | Award Contract for Heat Pump | 0 | Project Controls
EC1070 | EC1180 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish.Brick Brick | Review and Approve Brick Samples | Prepare and Solicit Bids for Brick Exterior | 0 | KimP | Project Controls
EC1180 | EC1220 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish.Brick Brick | Prepare and Solicit Bids for Brick Exterior | Review Bids for Brick | 0 | Project Controls | Project Controls
EC1220 | EC1260 | FS | Completed | In Progress | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish.Brick Brick | Review Bids for Brick | Award Contract for Brick | 0 | Project Controls | Project Controls
EC1030 | EC1040 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.D&E Design and Engineering | EC00515.Ex-Finish.Brick Brick | Review and Approve Designs | Assemble Brick Samples | 0 | KimP
EC1030 | EC1050 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.D&E Design and Engineering | EC00515.D&E Design and Engineering | Review and Approve Designs | Assemble Technical Data for Heat Pump | 0 | KimP | KimP
EC1050 | EC1160 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.D&E Design and Engineering | EC00515.D&E Design and Engineering | Assemble Technical Data for Heat Pump | Review Technical Data on Heat Pumps | 0 | KimP | KimP
EC1030 | EC1060 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.D&E Design and Engineering | EC00515.Int-Finish.Coverings Floor and Carpeting | Review and Approve Designs | Assemble and Submit Flooring Samples | 0 | KimP
EC1000 | EC1030 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.D&E Design and Engineering | EC00515.D&E Design and Engineering | Design Building Addition | Review and Approve Designs | 0 | KimP | KimP
EC1040 | EC1070 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish.Brick Brick | Assemble Brick Samples | Review and Approve Brick Samples | 0 |  | KimP
EC1270 | EC1290 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.HVAC HVAC | Award Contract for Heat Pump | Fabricate and Deliver Heat Pump and Controls | 0 |  | Project Controls
EC1060 | EC1080 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.Int-Finish.Coverings Floor and Carpeting | EC00515.Int-Finish.Coverings Floor and Carpeting | Assemble and Submit Flooring Samples | Review and Approve Flooring | 0 |  | KimP
EC1260 | EC1280 | FS | In Progress | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish.Brick Brick | Award Contract for Brick | Deliver Brick | 0 | Project Controls
EC1300 | EC1310 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Coverings Floor and Carpeting | EC00515.Int-Finish.Coverings Floor and Carpeting | Award Contract for Flooring | Fabricate and Deliver Flooring | 0 | Project Controls | Project Controls
EC1030 | EC1090 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.D&E Design and Engineering | EC00515.Found Foundation | Review and Approve Designs | Begin Building Construction | 0 | KimP
EC1090 | EC1100 | SS | Completed | Completed | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Begin Building Construction | Site Preparation | 0 |  | Exc
EC1100 | EC1230 | FS | Completed | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Site Preparation | Excavation | 0 | Exc | Exc
EC1230 | EC1320 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Excavation | Install Underground Water Lines | 0 | Exc | Plumb
EC1230 | EC1330 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Excavation | Install Underground Electric Conduit | 0 | Exc | Elec
EC1320 | EC1340 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Install Underground Water Lines | Form/Pour Concrete Footings | 0 | Plumb | IrnWrk
EC1330 | EC1340 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Install Underground Electric Conduit | Form/Pour Concrete Footings | 0 | Elec | IrnWrk
EC1340 | EC1350 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Form/Pour Concrete Footings | Concrete Foundation Walls | 0 | IrnWrk | IrnWrk
EC1350 | EC1360 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Concrete Foundation Walls | Form and Pour Slab | 0 | IrnWrk | FCarp
EC1360 | EC1370 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Form and Pour Slab | Backfill and Compact Walls | 0 | FCarp | Exc
EC1370 | EC1380 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Found Foundation | Backfill and Compact Walls | Foundation Phase Complete | 0 | Exc
EC1390 | EC1410 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Erect Structural Frame | Begin Structural Phase | 0 | IrnWrk
EC1370 | EC1390 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Found Foundation | EC00515.Structure Structure | Backfill and Compact Walls | Erect Structural Frame | 0 | Exc | IrnWrk
EC1390 | EC1420 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Erect Structural Frame | Floor Decking | 0 | IrnWrk | IrnWrk
EC1430 | EC1460 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Concrete First Floor | Erect Stairwell and Elevator Walls | 0 | IrnWrk | GenLabor
EC1420 | EC1430 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Floor Decking | Concrete First Floor | 0 | IrnWrk | IrnWrk
EC1430 | EC1470 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Concrete First Floor | Concrete Basement Slab | 0 | IrnWrk | IrnWrk
EC1460 | EC1540 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Erect Stairwell and Elevator Walls | Structure Complete | 0 | GenLabor
EC1470 | EC1540 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Concrete Basement Slab | Structure Complete | 0 | IrnWrk
EC1550 | EC1590 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish Exterior Finishes | Brick Exterior Walls | Close-In Phase Begins | 0 | GenLabor
EC1280 | EC1550 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish.Brick Brick | Deliver Brick | Brick Exterior Walls | 0 |  | GenLabor
EC1540 | EC1550 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Ex-Finish.Brick Brick | Structure Complete | Brick Exterior Walls | 0 |  | GenLabor
EC1550 | EC1560 | SS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish.Win Doors and Windows | Brick Exterior Walls | Install Door and Window Frames | 5 | GenLabor | FCarp
EC1550 | EC1600 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Brick Brick | EC00515.Ex-Finish.Roof Roof | Brick Exterior Walls | Insulation and Built-up Roofing | 0 | GenLabor | GenLabor
EC1580 | EC1600 | FF | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Win Doors and Windows | EC00515.Ex-Finish.Roof Roof | Install Exterior Doors and Windows | Insulation and Built-up Roofing | 0 | FCarp | GenLabor
EC1560 | EC1580 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Win Doors and Windows | EC00515.Ex-Finish.Win Doors and Windows | Install Door and Window Frames | Install Exterior Doors and Windows | 0 | FCarp | FCarp
EC1600 | EC1620 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Roof Roof | EC00515.Ex-Finish Exterior Finishes | Insulation and Built-up Roofing | Building Enclosed | 0 | GenLabor
EC1580 | EC1620 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish.Win Doors and Windows | EC00515.Ex-Finish Exterior Finishes | Install Exterior Doors and Windows | Building Enclosed | 0 | FCarp
EC1440 | EC1490 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.Systems Plumbing and Electrical | EC00515.Mechanicals Mechanical/Electrical Systems | Set Mechanical and Electrical Equipment | Rough-In Phase Begins | 0 | Operator
EC1430 | EC1440 | SS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Mechanicals.Systems Plumbing and Electrical | Concrete First Floor | Set Mechanical and Electrical Equipment | 7 | IrnWrk | Operator
EC1440 | EC1500 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.Systems Plumbing and Electrical | EC00515.Mechanicals.HVAC HVAC | Set Mechanical and Electrical Equipment | Install HVAC Ducts | 0 | Operator | HVAC
EC1620 | EC1630 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish Exterior Finishes | EC00515.Mechanicals.HVAC HVAC | Building Enclosed | Insulate Ducts | 0 |  | HVAC
EC1500 | EC1630 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.HVAC HVAC | Install HVAC Ducts | Insulate Ducts | 0 | HVAC | HVAC
EC1290 | EC1650 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.HVAC HVAC | Fabricate and Deliver Heat Pump and Controls | Set Heat Pump | 0 | Project Controls | Operator
EC1620 | EC1650 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish Exterior Finishes | EC00515.Mechanicals.HVAC HVAC | Building Enclosed | Set Heat Pump | 0 |  | Operator
EC1630 | EC1650 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.HVAC HVAC | Insulate Ducts | Set Heat Pump | 0 | HVAC | Operator
EC1500 | EC1510 | SS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.Systems Plumbing and Electrical | Install HVAC Ducts | Rough-In Plumbing/Piping | 4 | HVAC | Plumb
EC1620 | EC1640 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish Exterior Finishes | EC00515.Mechanicals.Systems Plumbing and Electrical | Building Enclosed | Install Wiring and Cable | 0 |  | Elec
EC1510 | EC1640 | SS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.Systems Plumbing and Electrical | EC00515.Mechanicals.Systems Plumbing and Electrical | Rough-In Plumbing/Piping | Install Wiring and Cable | 5 | Plumb | Elec
EC1460 | EC1520 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Mechanicals.Lifts Elevator | Erect Stairwell and Elevator Walls | Install Elevator Rails and Equipment | 0 | GenLabor | Elev Inst
EC1650 | EC1660 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.Systems Plumbing and Electrical | Set Heat Pump | Connect Equipment | 0 | Operator
EC1640 | EC1660 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.Systems Plumbing and Electrical | EC00515.Mechanicals.Systems Plumbing and Electrical | Install Wiring and Cable | Connect Equipment | 0 | Elec
EC1660 | EC1680 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.Systems Plumbing and Electrical | EC00515.Mechanicals.HVAC HVAC | Connect Equipment | Startup and Test HVAC | 0 |  | Operator
EC1520 | EC1690 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.Lifts Elevator | EC00515.Mechanicals Mechanical/Electrical Systems | Install Elevator Rails and Equipment | Rough In Complete | 0 | Elev Inst
EC1680 | EC1690 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals Mechanical/Electrical Systems | Startup and Test HVAC | Rough In Complete | 0 | Operator
EC1620 | EC1700 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish Exterior Finishes | EC00515.Int-Finish Interior Finishes | Building Enclosed | Drywall in Offices | 0 |  | FCarp
EC1690 | EC1700 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals Mechanical/Electrical Systems | EC00515.Int-Finish Interior Finishes | Rough In Complete | Drywall in Offices | 0 |  | FCarp
EC1700 | EC1740 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish Interior Finishes | EC00515.Int-Finish.Carp Carpentry | Drywall in Offices | Install Ceiling Grid | 0 | FCarp | FCarp
EC1740 | EC1760 | SS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Carp Carpentry | EC00515.Int-Finish.Fixtures Plumbing and Lighting Fixtures | Install Ceiling Grid | Install Lighting Fixtures | 8 | FCarp | Elec
EC1740 | EC1770 | SS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Carp Carpentry | EC00515.Mechanicals.HVAC HVAC | Install Ceiling Grid | Install AC Grills and Registers | 8 | FCarp
EC1310 | EC1790 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Coverings Floor and Carpeting | EC00515.Int-Finish.Coverings Floor and Carpeting | Fabricate and Deliver Flooring | Install Floor and Carpeting | 0 | Project Controls | Floor
EC1740 | EC1790 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Carp Carpentry | EC00515.Int-Finish.Coverings Floor and Carpeting | Install Ceiling Grid | Install Floor and Carpeting | 0 | FCarp | Floor
EC1760 | EC1790 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Fixtures Plumbing and Lighting Fixtures | EC00515.Int-Finish.Coverings Floor and Carpeting | Install Lighting Fixtures | Install Floor and Carpeting | 0 | Elec | Floor
EC1770 | EC1790 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Int-Finish.Coverings Floor and Carpeting | Install AC Grills and Registers | Install Floor and Carpeting | 0 |  | Floor
EC1790 | EC1800 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Coverings Floor and Carpeting | EC00515.Int-Finish.Carp Carpentry | Install Floor and Carpeting | Finish Carpentry and Millwork | 0 | Floor | FCarp
EC1790 | EC1810 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Coverings Floor and Carpeting | EC00515.Int-Finish.Fixtures Plumbing and Lighting Fixtures | Install Floor and Carpeting | Install Plumbing Fixtures | 0 | Floor | Plumb
EC1620 | EC1710 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Ex-Finish Exterior Finishes | EC00515.Mechanicals.Lifts Elevator | Building Enclosed | Install Elevator Cab and Finishes | 0 |  | Elev Inst
EC1690 | EC1710 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals Mechanical/Electrical Systems | EC00515.Mechanicals.Lifts Elevator | Rough In Complete | Install Elevator Cab and Finishes | 0 |  | Elev Inst
EC1700 | EC1720 | SS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish Interior Finishes | EC00515.Int-Finish.Paint Paint | Drywall in Offices | Paint Building Interior | 7 | FCarp | Paint
EC1800 | EC1820 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Carp Carpentry | EC00515.Int-Finish Interior Finishes | Finish Carpentry and Millwork | Touch-up and Clean-up | 0 | FCarp | FCarp
EC1810 | EC1820 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Fixtures Plumbing and Lighting Fixtures | EC00515.Int-Finish Interior Finishes | Install Plumbing Fixtures | Touch-up and Clean-up | 0 | Plumb | FCarp
EC1710 | EC1820 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.Lifts Elevator | EC00515.Int-Finish Interior Finishes | Install Elevator Cab and Finishes | Touch-up and Clean-up | 0 | Elev Inst | FCarp
EC1720 | EC1820 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish.Paint Paint | EC00515.Int-Finish Interior Finishes | Paint Building Interior | Touch-up and Clean-up | 0 | Paint | FCarp
EC1820 | EC1830 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish Interior Finishes | EC00515.Mechanicals.HVAC HVAC | Touch-up and Clean-up | Test and Balance HVAC Equipment | 0 | FCarp | Operator
EC1830 | EC1840 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Int-Finish Interior Finishes | Test and Balance HVAC Equipment | Finishes Complete | 0 | Operator
EC1840 | EC1850 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish Interior Finishes | EC00515.Int-Finish Interior Finishes | Finishes Complete | Punch List | 0 |  | Paint
EC1850 | EC1860 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Int-Finish Interior Finishes | EC00515.Int-Finish Interior Finishes | Punch List | Building Addition Complete | 0 | Paint
EC1650 | EC1670 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.HVAC HVAC | Set Heat Pump | Relocate HVAC Chiller | 0 | Operator | Operator
EC1670 | EC1680 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals.HVAC HVAC | EC00515.Mechanicals.HVAC HVAC | Relocate HVAC Chiller | Startup and Test HVAC | 0 | Operator | Operator
EC1430 | EC1480 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Concrete First Floor | Concrete Second Floor | 0 | IrnWrk | IrnWrk
EC1010 | EC1000 | FS | Completed | Completed | EC00515 | EC00515 | EC00515.D&E Design and Engineering | EC00515.D&E Design and Engineering | Start Office Building Addition Project | Design Building Addition | 0 |  | KimP
EC1490 | EC1680 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals Mechanical/Electrical Systems | EC00515.Mechanicals.HVAC HVAC | Rough-In Phase Begins | Startup and Test HVAC | 0 |  | Operator
EC1490 | EC1520 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Mechanicals Mechanical/Electrical Systems | EC00515.Mechanicals.Lifts Elevator | Rough-In Phase Begins | Install Elevator Rails and Equipment | 0 |  | Elev Inst
EC1480 | EC1540 | FS | Not Started | Not Started | EC00515 | EC00515 | EC00515.Structure Structure | EC00515.Structure Structure | Concrete Second Floor | Structure Complete | 0 | IrnWrk

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Hour ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=m/d/yyyy CurrencyFormat=US Dollar